Proprietary

ARPA-H Mission Office Solution Summary

Decoding the Immune Trajectory:

A Universal Ambulatory Cytokine Monitoring Platform

| Innovative Solutions Opening Title | ARPA-H Proactive Health Office Mission Office ISO — ARPA-H-SOL-24-106 |
| --- | --- |
| Solution Summary Title | Decoding the Immune Trajectory: A Universal Ambulatory Cytokine Monitoring Platform |
| Submitter Organization | Proactive Dx Inc. (aka, Biomarkr) |
| Type of Organization | ☑ For-Profit ☐ Non-profit ☐ Academia |
| Technical Point of Contact (POC) | Reuven Duer, PhD — CSO & Co-Founder 192 Odebolt Drive, Thousand Oaks, CA 91360 Telephone: 805-4054620 Email: reuven@biomarkr.health |
| Administrative POC | Dylan Brownstein — CEO Email: dylan@biomarkr.health |
| Estimated Project Duration | 24 Months |
| Total Basis of Estimate | Total: $4,800,000 |
| Resource Sharing (if applicable) | Gov’t: N/A Performer: N/A |
| Place(s) of Performance | Thousand Oaks, California, USA |

SUB-AWARDEE AND CONSULTANT TEAM MEMBERS

Organization Name: SMC Ltd. (smcltd.com) — Development & Manufacturing Partner Technical POC Name: TBD ¦ Organization Type: For-Profit (ISO 13485-certified CDMO) Organization Name: CRO (TBD upon award) — Clinical Study Operations Technical POC Name: TBD ¦ Organization Type: For-Profit Organization Name: MCRA, an IQVIA business — Regulatory Affairs & Clinical Validation Partner Technical POC: James Mullally, PhD (VP, IVD Regulatory Affairs); Julie Martel, PhD (VP, IVD Clinical Affairs) ¦ Organization Type: For-Profit (IQVIA company)

# Concept Summary

Biomarkr proposes to complete engineering and clinical feasibility validation of Q-SENS, a palm-sized silicon photonic biosensor that simultaneously quantifies five cytokines (IL-6, TNF-α, IL-1β, IFN-γ, IL-10) from a 10 µL fingerstick whole blood sample in under 10 minutes. The platform delivers single pg/mL sensitivity in whole blood, validated against Luminex, without sample preparation, centrifugation, or laboratory infrastructure. Built on 22 issued US patents, it has been validated at prototype stage through a prior BARDA DRIVe award (“Bringing Laboratory Testing to the Home” AOI).

This proposal directly addresses PHO interest area 1(ii): “methods for continuous and widespread sensing of health-state and early disease indicators deployable at population scale.” The specific engineering challenge ARPA-H funding enables is transforming Q-SENS into a trajectory-aware immune monitoring platform, one that establishes personalized, circadian-normalized cytokine baselines per individual and detects immunological deviations days before clinical symptoms manifest.

BARDA validated that home-based cytokine testing is feasible. ARPA-H funds the trajectory-intelligence layer: the pre-competitive engineering and clinical feasibility work that private capital cannot efficiently fund at this stage.

# Innovation and Impact

## The Case for Home-Based Immune Monitoring

Chronic inflammatory diseases - RA, IBD, Long COVID, cardiovascular disease - affect 100M+ Americans and cost >$800B/year. They are managed reactively: a flare presents, a treatment is adjusted, damage has already occurred. The root cause is not a lack of effective drugs. It is the absence of a tool that can track immune dynamics in the patient’s daily environment.

Cytokine levels in inflammatory disease fluctuate on timescales of hours to days. A quarterly clinic visit or even a monthly blood draw is structurally unable to capture the immune trajectory that determines whether a biologic is working, whether a flare is building, or whether a patient’s immune system is recovering or deteriorating. The CGM transformed diabetes management not because glucose was a new biomarker, but because frequency of measurement transformed a snapshot into actionable trajectory data. Q-SENS does the same for the immune system.

Critical unmet gap: No current device achieves multiplexed cytokine quantification at home. Lab-based ELISA requires venipuncture, 24–72 hours, and $200–$800/panel. Luminex (the current gold standard) is lab-bound, operator-dependent, and requires serum separation. Q-SENS is the first platform to close this gap.

## Platform Technology: Silicon Photonic Biosensor

Q-SENS detection is based on evanescent wave optical sensing on a silicon photonic chip containing 32 sensors per cartridge. Each sensor is functionalized with a cytokine-specific capture antibody. When an analyte binds, a fluorescently labelled secondary antibody binds to it creating a fluorescent sandwich immunoassay, increasing the fluorescent signal. This signal increase is quantified in real time without enzymatic amplification, wash steps, or liquid reagent handling by the user.

The fluorescent sandwich immunoassay format, adapted for evanescent wave excitation, achieves single pg/mL sensitivity in unprocessed whole blood, validated in head-to-head comparison against Luminex bead-based multiplex assay. The 32-sensor chip architecture supports simultaneous measurement of up to 32 biomarkers, with the current 5-cytokine panel occupying 5 sensor clusters (5 analytes × 5 replicate sensors + calibrators). Expanding to additional panels, cardiovascular, oncology, pandemic preparedness, requires cartridge reformulation only, with no hardware redesign of the reader.

| Parameter | Q-SENS Specification | Current Lab Standard | Clinical Significance |
| --- | --- | --- | --- |
| Analytes | 5 cytokines simultaneously (IL-6, TNF-α, IL-1β, IFN-γ, IL-10) | Single analyte per test (ELISA) or 5-plex on Luminex (lab-bound) | Full cytokine axis coverage in one fingerstick |
| Sample | 10 µL fingerstick whole blood, no sample prep required | 2–5 mL venipuncture; centrifuge + dilution required | Enables truly home-based testing |
| Sensitivity | Single pg/mL in whole blood (validated vs. Luminex); an order of magnitude further improvement is expected in the final optimized design | 1–10 pg/mL (ELISA, serum); ~1 pg/mL (Luminex, serum) | Equivalent sensitivity at POC without lab infrastructure |
| Time to result | <10 minutes | 24–72 hours (central lab) | Enables same-visit clinical decision support |
| Detection principle | Evanescent wave excitation and collection of fluorescent signals (32 sensors/chip) | Plate ELISA or bead-based Luminex fluorescence | No enzymatic amplification steps, no sample prep., no wash steps |
| Platform scalability | 32 sensors per chip; expandable panel without hardware redesign | New instrument required for each additional analyte class | Future panels (CVD, oncology, pandemic) on same reader |
| Cartridge | Single-use, closed-system fluidics; no wash steps; ambient storage | Multiple reagent tubes; cold-chain dependent | Patient-operable; no training required beyond fingerstick |

The three panels in Figure 1 illustrate the core scientific premise of this proposal. Each chart shows a different immune trajectory pattern detectable only through longitudinal Q-SENS monitoring, invisible to single-timepoint testing. Left: cytokine rise 3–5 days before clinical RA flare onset, demonstrating the pre-symptomatic detection window that enables early intervention. Center: the 2–4-fold circadian variation in IL-6 and TNF-α that must be individually characterized and wake-normalized before true immune deviations can be distinguished from circadian noise. Right: the episodic dysregulation pattern of Long COVID, distinguished from recovery by a blunted counter-regulatory IL-10 response.

Figure 1. Simulated cytokine trajectories (literature-based). Left: RA pre-symptomatic flare, IL-6 & TNF-α rise 3–5 days before symptom onset, enabling early intervention. Center: Individual circadian variation in IL-6 and TNF-α; without wake-normalized personal correction, 40% of apparent deviations are circadian noise. Right: Long COVID episodic immune dysregulation with blunted IL-10. All signatures are trajectory-dependent, not threshold-dependent.

AI/ML as a critical enabler. The trajectory patterns shown in Figure 1 cannot be detected, interpreted, or acted upon without machine learning. Unlike a single biomarker threshold, where a number above a cutoff triggers a decision, longitudinal cytokine trajectories are inherently high-dimensional: five analytes, measured repeatedly over weeks, each with individual circadian variation, inter-day noise, and disease-specific dynamics. The clinically meaningful signal lives not in any individual reading but in features that require algorithmic extraction: rate of change of each cytokine relative to that individual’s personal baseline, cytokine ratios (e.g., IL-6:IL-10 as a measure of counter-regulatory balance; IFN-γ:TNF-α as a Th1/innate ratio), and the temporal co-evolution of multiple markers as a system signature. No physician, and no single-analyte diagnostic rule, can process this information from snapshot measurements. ML models trained on personalized longitudinal Q-SENS data are the first tool capable of doing so, and this program generates the dataset required to build and validate them.

## Competitive Comparison

| Capability | Current State-of-Art | Q-SENS Year 1 | Q-SENS Year 2 (Goal) |
| --- | --- | --- | --- |
| 5-plex cytokine POC | Not possible | Prototype validated | RUO commercial; 510(k) filed |
| Sensitivity in whole blood | ~100–1000 pg/mL (POCT strips) | Single pg/mL vs. Luminex | Sub pg/mL, validated |
| Sample prep required | Yes (centrifuge + dilute) | None | None |
| Circadian normalization | None in any system | Algorithm developed | Validated (n=30 normals) |
| Flare prediction lead time | 0 (reactive) | Feasibility model | AUC ≥0.80, ≥5 days |
| Cost per 5-plex panel | $200–$800 (central lab) | ~$15 RUO cartridge | <$15 at scale |

## Primary Use Cases

| Use Case | Unmet Need & Q-SENS Impact |
| --- | --- |
| RA — Biologic Monitoring & Flare Prediction | 1.5M US patients on biologics have no objective home monitoring. Q-SENS trajectories detect treatment response within days and predict flares 5–7 days before clinical presentation, enabling dose adjustment before joint damage occurs. |
| Long COVID / ME-CFS — Objective Phenotyping | 17M+ Americans with Long COVID have no FDA-cleared objective biomarker. Episodic IFN-γ and IL-6 trajectory patterns provide the first immune fingerprint, enabling trial stratification and treatment response monitoring. |
| IBD — Treatment Response Between Infusions | 3M+ IBD patients assessed clinically every 8–12 weeks. Q-SENS detects secondary loss-of-response before clinical relapse, enabling proactive biologic switching rather than reactive dose escalation. |
| Pharma / Decentralized Clinical Trials | Immune-modulating biologic trials measure PD effect at site visits every 4–12 weeks. Q-SENS provides continuous remote pharmacodynamic data between visits, compressing timelines and enabling proof-of-concept at lower N. |
| Proactive Immune Surveillance | Post-surgical, cardiovascular risk, and cancer survivor populations carry chronic low-grade inflammation invisible to standard labs. Longitudinal Q-SENS monitoring detects smoldering activation before organ damage. |
| Academic & Translational Research | Exercise, nutrition, aging, sleep, and vaccine response researchers rely on ELISA (72-hour, single-plex). Q-SENS enables frequent, standardized, ambulatory 5-plex cytokine collection at scale. |

# Proposed Work

Final deliverable: A clinically validated, trajectory-aware Q-SENS platform with: (1) circadian-aware firmware and personalized baseline algorithm; (2) normative circadian cytokine profiles from 30 healthy volunteers; (3) published feasibility evidence of pre-symptomatic flare prediction in 60 patients (30 RA + 30 Long COVID).

| Period | Milestone | Deliverable | Go/No-Go Metric |
| --- | --- | --- | --- |
| M0–M6 | Platform engineering: circadian-aware firmware, personalized baseline algorithm with phase-correction, cartridge precision optimization. | Algorithm documentation; bench validation report. | CV <8% all 5 cytokines at clinical concentrations. |
| M6–M12 | Circadian characterization (n=30 healthy volunteers): 14-day 6x/day wake-normalized protocol; validate phase-correction vs. Luminex & ELISA. | Individual circadian profiles; phase-correction validation dataset. | Pearson r >0.90 vs. reference assay. |
| M12–M20 | Feasibility cohort (n=60: RA 30 + Long COVID 30): 6-month 2x/week home monitoring + monthly nurse visit; capture ≥3 confirmed flares/arm; train trajectory deviation model. | Longitudinal dataset; ML model; primary endpoint analysis. | AUC ≥0.80 for flare detection ≥5 days pre-onset. |
| M20–M24 | Analysis, publications, scale-up readiness; dataset prepared for large-scale government-funded trial grant. | 2 manuscripts submitted; curated longitudinal dataset. | 2 peer-reviewed manuscripts submitted. |

## Technical Risks & Mitigations

- Risk 1: Cartridge precision at low cytokine concentrations - on-chip calibration spots and lot-specific firmware curves.

- Risk 2: Participant adherence to 6x/day circadian protocol - video supervision and completion-linked incentive payments.

- Risk 3: Flare capture within 6-month window - enroll only patients with ≥2 confirmed flares/year; interim analysis at Month 4.

- Risk 4: RUO data firewall - results not returned to participants for clinical use; IRB consent process addresses this explicitly.

# Team Organization and Capabilities

| Name / Role | Background & Relevance |
| --- | --- |
| Reuven Duer, PhD CSO & Co-Founder (PI) | Inventor of Q-SENS. 22 issued US patents covering silicon photonic immunoassay: evanescent wave fluorescence immunoassay (“ELISA on a chip”), fluidic cartridge, and multiplexed biosensing. Led R&D from concept through BARDA-validated prototype. Leads platform engineering (M0–M12) and data quality oversight. |
| Dylan Brownstein CEO | Responsible for program management, budget oversight, milestone reporting, and ARPA-H relationship. |
| Aren Giske, MD, MOH, FACOEM COO & Co-Founder | Leads IRB submission, human subjects compliance, and clinical protocol for the feasibility cohort. |
| SMC Ltd. (smcltd.com) Development & Manufacturing Partner | ISO 13485-certified, FDA-registered CDMO specializing exclusively in medical diagnostics and POC devices. In-house specialists in microfluidic cartridge design and disposable POC consumables. Prior experience bringing POC cartridges from prototype to commercial readiness, including a sepsis pathogen detection POC device. 11 global facilities (US, UK, India, Costa Rica). Provides cartridge development, scale-up manufacturing, supply chain management, and regulatory documentation support for Q-SENS. |
| MCRA, an IQVIA business Regulatory Affairs & Clinical Validation Partner | Global CRO + Advisory Firm (an IQVIA business). Engaged for FDA regulatory strategy and submissions (510(k) hsCRP; De Novo 5-cytokine CIP) and clinical validation study execution (Q-SENS CRP IVD Study). Team includes Dr. James Mullally, PhD (former FDA Assistant Director, Division of Chemistry and Toxicology Devices; VP IVD Regulatory Affairs) and Dr. Julie Martel, PhD (former Global Head of Clinical Operations, Ascensia Diabetes/CGM; VP IVD Clinical Affairs). 25+ former FDA officials; 100% PMA approval rate; 78 IVD studies managed in 7 years. Active proposals in hand: MCRA regulatory proposal (Ref. 20026538) and IQVIA MedTech clinical proposal (Ref. SAB95096). |

| Clinical Study Director (hire Month 1) MD/PhD — Rheumatology or Immunology | Clinical protocol oversight, site relationships, and medical monitoring for the 60-patient feasibility cohort. Target: academic medical center with established RA and Long COVID programs. |
| --- | --- |
| Biostatistician (hire Month 3) 0.5 FTE | Longitudinal biomarker study design, repeated-measures models, and ML classifier validation. Pre-specified Statistical Analysis Plan and primary endpoint analysis (flare prediction AUC). |

# Basis of Estimate (BOE)

Milestone-gated: $1.8M at contract execution; $1.5M at M6 go/no-go; $1.5M at M12 go/no-go.

| Cost Element | Amount | Basis |
| --- | --- | --- |
| Personnel (PI, CEO liaison, Clinical Study Director 1.0 FTE, Biostatistician 0.5 FTE, Research Associate 1.0 FTE) | $1,140,000 | Burdened labor rates; 3.0 FTE equivalent over 24 months |
| Platform Engineering incl. SMC Ltd. cartridge development (firmware, algorithm, cartridge R&D, bench validation) | $920,000 | SMC CDMO quote-basis; prior BARDA engineering milestones |
| Clinical Study Operations (CRO, IRB, coordination, 90 participants) | $980,000 | Comparable 90-participant POC device feasibility studies |
| Cartridges & Consumables (~18,000 tests via SMC manufacturing) | $720,000 | Pre-commercial RUO manufacturing cost at SMC |
| Laboratory Validation (Luminex/ELISA reference testing, data management, biostatistics) | $480,000 | Reference lab fee schedules + software |
| Participant Incentives (90 participants × ~$600) | $54,000 | IRB-standard compensation for comparable monitoring burden |
| Indirect Costs / Overhead (15%) | $506,000 | Applied to direct cost base |
| TOTAL BASIS OF ESTIMATE | $4,800,000 | 24 months |

| Basis of Estimate (BOE) | Amount |
| --- | --- |
| Total | $4,800,000 |
| Resource Sharing (if applicable) | Not applicable at this time |

Proprietary — Biomarkr, Inc.  |  ARPA-H-SOL-24-106  |  June 2026